## Minutes of Meeting-
Meeting Minutes
Meeting | Date | Participants | Name of the owner | Deadline | Status | Comments | Links
1 | 17.07.2026 | Hans Ehm, Abdelgafar Ismail, Excellence program Students , Botho Schanze, Tim , Hans , Wilfried , Ana | Name(s) of responsible(s) | DD.MM.YYYY
Item # | Item Type | Topics | Owners | Deadline | Status | Comments | Links
1 | Info | Kick off of the Excellence program Presentation of the Timeline | Abdo, Tim, Botho | - | Done
2 | Info | Tasks distribution | Abdo | - | Done
3 | Task | Plants | Esther | - | Ongoing
4 | Task | Water Supply | Phares | - | Ongoing
5 | Task | Product Transformation | Abdoul | - | Ongoing
6 | Task | Crop storage | Christelle | - | Ongoing
7 | Task | Energy Supply | Aida | - | Ongoing
8 | Task | Visitor Management | Alix | - | Ongoing
9 | Task | Fencing and security | Filomene | - | Ongoing
10 | Task | Machinery | Jean-Louis | - | Ongoing
11 | Task | Sales and Marketing | Marieta | - | Ongoing
12 | A/I | ‒Study the sustainable farm from last year ‒Use it as foundation for the new project ‒Everyone focus on his task with possibility to brainstorm together as a team ‒Next week: summarize what you worked on during the week and update your homepage | Students |  | Ongoing
2 | 24.07.2026 | Hans Ehm, Abdelgafar Ismail, Excellence program Students , Botho Schanze, Tim , Hans , Wilfried , Ana…. | Name(s) of responsible(s) | DD.MM.YYYY
Item # | Item Type | Topics | Owners | Deadline | Status | Comments | Links
1 | Info | Presentation | all | - | Done
2 | Feedback info | Christelle: Crops storage: thank you for the very good updates Good that you thought of the most important aspects of the storage Did you consider the storage capacity from previous year – and show a status of the capacity in the app | Hans and Abdo | - | Done
3 | Feedback info | Mariata: Sales & marketing: thank you for the very good updates Good job to research into what is existing already this is called state of the art – I recommend it as best practice Please look at what are the challenges to create an app | Hans and Abdo | - | Done
4 | Feedback info | Tania: Face recognition: thank you for the very good updates Good job to start with improving and enhancing the previous work – also recommend it as best practive | Hans and Abdo | - | Done
5 | Feedback info | Abdoul: Product transform: thank you for the very good updates Good job to study and reverse engineer previous solution – data model is very good step as well – please share a screenshot of it next time Did you think of how the app should contain the most important aspects of product transformation | Hans and Abdo | - | Done
6 | Feedback info | Ester: Plants: thank you for the very good updates Good job to review the previous work – do plausi check for the calculation in excel – thank you for fixing the error As next step I would recommend to list what are the important aspects of the plants app – you already did first step – think which aspects are needed for which partner downstream in the supply chain | Hans and Abdo | - | Done
7 | Feedback info | Phares: Irrigation system: thank you for the very good updates Good job to research into what is existing already this is called state of the art I would recommend to focus on designing the app to make more water saving planning | Hans and Abdo | - | Done
8 | Feedback info | Jean-Louis: Equipment: thank you for the very good updates Good job to research into what is existing already this is called state of the art One of the most important aspects of machine is utilization and maintenance I would recommend to include in the app | Hans and Abdo | - | Done
9 | Feedback info | Aida: Not in the call | Hans and Abdo | - | Done
10 | Feedback info | Alix: Not in the call | Hans and Abdo | - | Done
3 | 31.07.2026 | Hans Ehm, Abdelgafar Ismail, Excellence program Students , Botho Schanze, Tim , Hans , Wilfried , Ana…. | Name(s) of responsible(s) | DD.MM.YYYY
Item # | Item Type | Topics | Owners | Deadline | Status | Comments | Links
1 | Info | Presentation | all | - | Done
2 | Feedback info | Esther: all clear - thanks Plants: thank you for using Miro to break down your tasks, I gave you feedback in Miro, next step is to execute the steps Start with a general mockup like the others and proceed task by task Great to use the data base feature Regarding putting together the apps – this we didn’t nominate a person yet it we will see based on how fast | Hans and Abdo | - | Done
3 | Feedback info | Phares: content well understood – it would be better to use a white color on the blue background Irrigation system: Thank you for working on water-saving irrigiation, the link does not work in your homepage Next steps: use Miro board to break down your tasks and create a mock-up of your app | Hans and Abdo | - | Done
4 | Feedback info | Rayane: all clear – thanks Equipment: your Mockup looksvery good, interactive and different taps What I think missing is the equipment utilization in percentage The ERD looks good as well, but I would recommend to use a concept like 4M Machine, Method, Material & human Question about the stack which will be used to build the app | Hans and Abdo | - | Done
5 | Feedback info | Aida: content well understood – for the hyperlink you can use a clear text like “Energy system” Nice to have you in the call this week: please use Miro to break down your tasks It is very good to add energy backup & carbon footprint Next please create a mock-up | Hans and Abdo | - | Done
6 | Feedback info | Alix: content well understood: – for the hyperlink you can use a clear text like “Visitor Management System” and “Mockup” Nice to have you in the call this week: Your mock-up looks very good – try to use similar fonts as the other mock-up (all apps need to use same fonts) Next step: please use Miro to break down your tasks | Hans and Abdo | - | Done
7 | Feedback info | Christelle: all clear – thanks, maybe you use a better bullte point (not one with a “?” inside the black diamond Crops storage: thank you for creating a Mock-up it looks good, but please move towards a more interactive version Use miro to break down your tasks – start with the first task directly | Hans and Abdo | - | Done
8 | Feedback info | Mariata: all clear – thanks Sales & marketing: thank you to work on the challenges, it looks very good Next step: Use miro to break down your tasks – start with the first task directly | Hans and Abdo | - | Done
9 | Feedback info | Tania: all good maybe remove the “?” Face recognition: if possible to translate your pdf into a mockup and use Miro Question about the app building: good question, make a plan in Miro and follow it step by step | Hans and Abdo | - | Done
10 | Feedback info | Abdoul: Product transform: your Mockup looksvery good, interactive and different taps Any possibility to get input from Plants app e.g. amount of Mango harvested, make a forecast based on historical values | Hans and Abdo | - | Done
4 | 07.08.2026 | Hans Ehm, Abdelgafar Ismail, Excellence program Students , Botho Schanze, Tim , Hans , Wilfried , Ana…. | Name(s) of responsible(s) | DD.MM.YYYY
Item # | Item Type | Topics | Owners | Deadline | Status | Comments | Links
1 | Info | Presentation | all | - | Done
2 | Feedback info | Rayane: thanks for the update. Maybe you can write out the abbreviation like CRUDE Feedback from last week: Equipment: your Mockup looksvery good, interactive and different taps – I like that you have dashboards and scorecards What I think missing is the equipment utilization in percentage – thanks for adding it it looks good now The ERD looks good as well, but I would recommend to use a concept like 4M Machine, Method, Material & human – thanks for adding it Question about the stack which will be used to build the app – I brought Anar to the call with his computer science he will be available to support your technical questions Feedback from this week: Please add a tab in your mock-up for what -if scenario analysis – e.g. say we want to add one more equipment what cost and benefits it brings you maybe show there | Hans and Abdo | - | Done
3 | Feedback info | Justine: well understood, good homepage; you have one label in a diamond at Project/Task which is a “?” on our screen. Please try to get it of. Feedback from last week: please add your updates to the homepage Nice to have you in the call this week: please use Miro to break down your tasks – thank you for adding your tasks in Miro It is very good to add energy backup & carbon footprint Next please create a mock-up Feedback for next week: Please add Mock up to the page | Hans and Abdo | - | Done
4 | Feedback info | Carine: well understood, all good Feedback from last week: Nice to have you in the call this week: Your mock-up looks very good – try to use similar fonts as the other mock-up (all apps need to use same fonts) – woow the mock-up looks very good now improved and matching the style Next step: please use Miro to break down your tasks Feedback for next week: Please add to the mock-up a tab related to events e.g. if the farm is hosting an event | Hans and Abdo | - | Done
5 | Feedback info | Christelle; quite well understood; The text could be improved, like no blank before the coma, Now “_in front of a word Feedback from last week: Crops storage: thank you for creating a Mock-up it looks good, but please move towards a more interactive version – woow also significant improvements from last week altought some tabs are not complete- I like that you have dashboards and scorecards Use miro to break down your tasks – start with the first task directly – thank you for filling Miro board Feedback for next week: Please add a tab in your mock-up for what -if scenario analysis – e.g. say we want to add more storage what is cost and benefits Good questions: instead of Infineon logo think as a group to make a logo for the farm – for the data use dummy data at the beginning | Hans and Abdo | - | Done
6 | Feedback info | Marita; quite some strange labels on your homepage Feedback from last week: Sales & marketing: thank you to work on the challenges, it looks very good Next step: Use miro to break down your tasks – start with the first task directly – thank you for filling Miro Feedback for next week: I would create a mock-up like the others | Hans and Abdo | - | Done
7 | Feedback info | Ben: quite some strange labels on your homepage Feedback from last week: Product transform: your Mockup look svery good, interactive and different taps – Mock-up style need to match styles of other apps – make it easy later when integrated all as one platform Any possibility to get input from Plants app e.g. amount of Mango harvested, make a forecast based on historical values – thank you for looking at the inputs from the other workstreams Feedback for next week: Identified cross-functional dependencies – best way to show such cross-function dependency is to build a swimlane diagram – please do it for next week | Hans and Abdo | - | Done
8 | Feedback info | Esther: black on blue is difficult to read Ester: Feedback from last week: Plants: thank you for using Miro to break down your tasks, I gave you feedback in Miro, next step is to execute the steps – also gave feedback this week Start with a general mockup like the others and proceed task by task – Mock-up looks very good and it is interactive Great to use the data base feature Regarding putting together the apps – this we didn’t nominate a person yet it we will see based on how fast Feedback for next week: Built and tested the first working version of the backend – please add what-if scenario e.g. if we want to increase our plants output what are the scenarios | Hans and Abdo | - | Done
9 | Feedback info | Phares: well understood, all good Feedback from last week: Irrigation system: Thank you for working on water-saving irrigation, the link does not work in your homepage Next steps: use Miro board to break down your tasks and create a mock-up of your app – Thank you for adding your tasks in Miro - I gave you feedback in Miro Feedback for next week: Thank you working on the backend – you are head of the others I would recommend you build a mock-up finalize it within the next weeks | Hans and Abdo | - | Done
10 | Feedback info | Tanial: Feedback from last week: Face recognition: if possible to translate your pdf into a mockup and use Miro Question about the app building: good question, make a plan in Miro and follow it step by step – thank you for filling the miro Feedback for next week: Couldn’t see your update on the homepage – as next step I would create the mock-up and add it to the homepage like the others | Hans and Abdo | - | Done
5 | 14.08.2026 | Hans Ehm, Abdelgafar Ismail, Excellence program Students , Botho Schanze, Tim , Hans , Wilfried , Ana…. | Name(s) of responsible(s) | DD.MM.YYYY
Item # | Item Type | Topics | Owners | Deadline | Status | Comments | Links
1 | Info | Next week: Final Mock-up presentation: In General Thank you for adopting a one logo for all the farm – if not yet please adopt by all in General I would recommend all of you to make your update as follows: show what you did this week, which feedback you incorporated from last week, what is the next steps for next week | all | - | Done
2 | Feedback info | Rayane: all Good thanks Feedback from last week: Equipment: Please add a tab in your mock-up for what -if scenario analysis – e.g. say we want to add one more equipment what cost and benefits it brings you maybe show there – looks good please name it scenario analysis and create also sliders and dynamics charts like Christelle Feedback from this week: For the FE&BE technology questions Anar will provide more information | Hans and Abdo | - | Done
3 | Feedback info | Justine: Feedback from last week: please add your updates to the homepage Next please create a mock-up – thank you for creating the mock-up Please add Mock up to the page Feedback for next week: The scenario analysis tab would be great to add interactive charts when the scenario changes the chart changes dynamically like Christelle – unfortunately couldn’t hear you today | Hans and Abdo | - | Done
4 | Feedback info | Carine: all Good thanks Feedback from last week: Nice to have you in the call this week: Your mock-up looks very good – try to use similar fonts as the other mock-up (all apps need to use same fonts) – woow the mock-up looks very good now improved and matching the style Next step: please use Miro to break down your tasks Feedback for next week: Please add to the mock-up a tab related to events e.g. if the farm is hosting an event | Hans and Abdo | - | Done
5 | Feedback info | Christelle: all Good thanks Feedback from last week: Crops storage: Use miro to break down your tasks – start with the first task directly – thank you for filling Miro board – I will give you feedback there directly and you will get answer to your email about Please add a tab in your mock-up for what -if scenario analysis – e.g. say we want to add more storage what is cost and benefits – the Scenario Analysis option looks good – what is the point at which benefits are more than costs? Good questions: instead of Infineon logo think as a group to make a logo for the farm – for the data use dummy data at the beginning – I checked the logo it looks good Feedback for next week: Could you please write in the homepage you next steps: and whether you need input for the next step and from whom? | Hans and Abdo | - | Done
6 | Feedback info | Mariata: all Good thanks Feedback from last week: Sales & marketing: I would create a mock-up like the others – Thank you for creating the Mock-up it looks great – please use the same style like your colleagues and also add scenario analysis to the mock-up Feedback for next week: The forecasting model looks good: could you incorporate in the mock-up and if possible show always the last three months actual sales and the forecast for the next 12 months | Hans and Abdo | - | Done
7 | Feedback info | Tania: Feedback from last week: Face recognition: Couldn’t see your update on the homepage – as next step I would create the mock-up and add it to the homepage like the others – thank you for working on the mock-up it looks great Feedback for next week: Could you implement the mock-up from power point to web interface like the others and use the style of the others – unfortunately could hear you today | Hans and Abdo | - | Done
8 | Feedback info | Ben: all Good thanks Feedback from last week: Product transform: Identified cross-functional dependencies – best way to show such cross-function dependency is to build a swimlane diagram – thank you for showing that Feedback for next week: What is the next step and please show it always in your homepage and what input you will use for it – Audio as breaking please improve for next time | Hans and Abdo | - | Done
9 | Feedback info | Esther: all Good thanks Feedback from last week: Plants: Built and tested the first working version of the backend – please add what-if scenario e.g. if we want to increase our plants output what are the scenarios – thank you for adding the scenario Analysis tab (name it as well like that) Feedback for next week: The scenario Analysis looks good but could you add sliders and dynamic charts like Christelle | Hans and Abdo | - | Done
10 | Feedback info | Phares: all Good thanks Feedback from last week: Irrigation system: Thank you working on the backend – you are head of the others I would recommend you build a mock-up finalize it within the next weeks – The mock-up looks great please make sure the style is similar to the others Feedback for next week: Please also create Scenario Analysis | Hans and Abdo | - | Done
6 | 21.08.2026 | Hans Ehm, Abdelgafar Ismail, Excellence program Students , Botho Schanze, Tim , Hans , Wilfried , Ana…. | Name(s) of responsible(s) | DD.MM.YYYY
Item # | Item Type | Topics | Owners | Deadline | Status | Comments | Links
1 | Info | General feedback: Mock-up looks very good please proceed to the next steps e.g. BE and database development could you have a summary dashboard on top showing the key performance indicators like what Justine showed on top for every category then there are specific tabs for more detailed views should we have guidelines for all pages e.g. font size or logo should have white background …etc. | all | - | Done
2 | Feedback info | Alix: thanks for the update on the dashboard; it would be interesting how you came to the data shown here; please also update your homepage of not done yet Mock-up looks very good congrats - Logo and style need to be consistent consistent e.g. font size is very small compared to the others | Hans and Abdo | - | Done
3 | Feedback info | Ben: thanks for the update on the dashboard; it would be interesting how you came to the data shown here; please also update your homepage of not done yet Mock-up looks very good congrats Logo is too small and style need to be consistent | Hans and Abdo | - | Done
4 | Feedback info | Phares: thanks for the update on the dashboard; it would be interesting how you came to the data shown here; please also update your homepage of not done yet Mock-up looks very good congrats Logo size also need to be appropriate | Hans and Abdo | - | Done
5 | Feedback info | Rayane: thanks for the update on the dashboard; it would be interesting how you came to the data shown here; please also update your homepage of not done yet Mock-up looks very good congrats Logo size also need to be appropriate | Hans and Abdo | - | Done
6 | Feedback info | Justine: Mock-up looks very good congrats -logo needs to have white background – she presented very good | Hans and Abdo | - | Done
7 | Feedback info | Christelle: thanks for the update on the dashboard; it would be interesting how you came to the data shown here; please also update your homepage of not done yet; on your y-axes what I the 5m (% million, always describe what you have on x- and y-axes) Mock-up looks very good congrats – logo and font size needs to be adjusted it is too small – search functionality/dark theme is very good idea | Hans and Abdo | - | Done
8 | Feedback info | Tania: thanks for the update on the dashboard; Mock-up looks very good congrats – please use style from the others, color, font and font size | Hans and Abdo | - | Done
9 | Feedback info | Esther: thanks for the update on the dashboard; it would be interesting how you came to the data shown here; please also update your homepage of not done yet Mock-up looks very good congrats - please use style from the others, color, font and font size | Hans and Abdo | - | Done
10 | Feedback info | Mariata: Not in the call | Hans and Abdo | - | Done
7 | 28.08.2026 | Hans Ehm, Abdelgafar Ismail, Excellence program Students , Botho Schanze, Tim , Hans , Wilfried , Ana…. | Name(s) of responsible(s) | DD.MM.YYYY
Item # | Item Type | Topics | Owners | Deadline | Status | Comments | Links
1 | Info | General feedback: share best practices and lessons learned when you learn something For any question regarding the stacks please reach out to Anar:Anar.Akhmedov@infineon.com | all | - | Done
2 | Feedback info | Rayane: Feedback from last week: Equipment: For the FE&BE technology questions Anar will provide more information – thank you for adding KPIs and data sources Feedback from this week: What is a machine registry – will you use machine learning for optimization of equipment? | Hans and Abdo | - | Done
3 | Feedback info | Justine: Feedback from last week: please add your updates to the homepage The scenario analysis tab would be great to add interactive charts when the scenario changes the chart changes dynamically like Christelle – unfortunately couldn’t hear you today Feedback for next week: Thank you for correcting the logo Well explained your BE progress – just ensure before developing the FE that mock-up is consistent with all | Hans and Abdo | - | Done
4 | Feedback info | Carine: Feedback from last week: Would it be possible to use the visitor management app as a marketing tool, it will give input to the sales and marketing platform of potential customers – e.g. a questionaries about the reason for the visit and if you spot a potential customer give this feedback to the sales and marketing team to initiate contact Feedback for next week: Thank you for fixing the logo and font style – for the database if you have questions address them to Anar | Hans and Abdo | - | Done
5 | Feedback info | Christelle: Feedback from last week: Crops storage: Could you please write in the homepage you next steps: and whether you need input for the next step and from whom? Feedback for next week: Thank you for addressing the feedback from us – for the BE and database | Hans and Abdo | - | Done
6 | Feedback info | Mariata: Feedback from last week: Sales & marketing: The forecasting model looks good: could you incorporate in the mock-up and if possible show always the last three months actual sales and the forecast for the next 12 months Feedback for next week: Thank you for reworking on the mock-up please finalize it this week and move to the BE part | Hans and Abdo | - | Done
7 | Feedback info | Tania: Feedback from last week: Face recognition: Could you implement the mock-up from power point to web interface like the others and use the style of the others – unfortunately could hear you today Feedback for next week: Thank you for implementing the feedback from us – moving to the FE and BE is a good step – approach Anar if you have questions | Hans and Abdo | - | Done
8 | Feedback info | Ben: Feedback from last week: Product transform: What is the next step and please show it always in your homepage and what input you will use for it – Audio as breaking please improve for next time Feedback for next week: Good progress, you already in FE Integration which means you already finished FE and BE and Database? | Hans and Abdo | - | Done
9 | Feedback info | Ester: Feedback from last week: Plants: The scenario Analysis looks good but could you add sliders and dynamic charts like Christelle Feedback for next week: Thank you for implementing the feedback – could you repeat your question | Hans and Abdo | - | Done
10 | Feedback info | Phares: Feedback from last week: Irrigation system: Please also create Scenario Analysis Feedback for next week: Thank you for working on the feedback – your next step check if you add a Scenario Analysis | Hans and Abdo | - | Done
8 | 04.09.2026 | Hans Ehm, Abdelgafar Ismail, Excellence program Students , Botho Schanze, Tim , Hans , Wilfried , Ana…. | Name(s) of responsible(s) | DD.MM.YYYY
Item # | Item Type | Topics | Owners | Deadline | Status | Comments | Links
1 | Info | General Feedback Coordinate with the other team members Make sure you communicate and coordinate with the people working on the other parts of the project, especially the backend team. The goal is to ensure that your module can be smoothly integrated into the final product without compatibility or integration issues. Explain all abbreviations Whenever you use an abbreviation or acronym on your homepage, always provide its full meaning the first time you mention it. This ensures that anyone viewing your homepage can understand the content, even if they are not familiar with the terminology. Clearly introduce your module At the beginning of your presentation, clearly state which module you are working on and briefly explain its purpose. This will help everyone understand the context of your presentation from the start. Questions about the tech stack If you have any questions or need clarification regarding the technology stack, frameworks, or tools being used, please reach out to Anar for guidance:Anar.Akhmedov@infineon.com | Hans and Anar | - | Done
2 | Feedback info | Christelle: very well explained and good homepage thanks | Hans and Anar | - | Done
3 | Feedback info | Mariata: maybe you can be more specific on your homepage what you mean with backend | Hans and Anar | - | Done
4 | Feedback info | Ben: good homepage but your voice was very low | Hans and Anar | - | Done
5 | Feedback info | Esther: On Project / Task be more specific wht it is … not veery reader knows what Taks 1-3; good voice & good homepage | Hans and Anar | - | Done
6 | Feedback info | Phares: good homepage and good voice | Hans and Anar | - | Done
7 | Feedback info | Madiega: be more specific project task on what you are working on | Hans and Anar | - | Done
8 | Feedback info | Tania: good homepage and good voice | Hans and Anar | - | Done
9 | Feedback info | Rayanne: Not in the call | Hans and Anar | - | Done
10 | Feedback info | Carine: Not in the call | Hans and Anar | - | Done
9 | 11.09.2026 | Hans Ehm, Abdelgafar Ismail, Excellence program Students , Botho Schanze, Tim , Hans , Wilfried , Ana…. | Name(s) of responsible(s) | DD.MM.YYYY
Item # | Item Type | Topics | Owners | Deadline | Status | Comments | Links
1 | Info | General Feedback Coordinate with the other team members Make sure you communicate and coordinate with the people working on the other parts of the project, especially the backend team. The goal is to ensure that your module can be smoothly integrated into the final product without compatibility or integration issues. Explain all abbreviations technical terms and tools Whenever you use an abbreviation or acronym, technical term, framework, or tool on your homepage, always provide its full meaning the first time you mention it. This ensures that anyone viewing your homepage can understand the content, even if they are not familiar with the terminology. Clearly introduce your module At the beginning of your presentation, clearly state which module you are working on and briefly explain its purpose. This will help everyone understand the context of your presentation from the start. | Hans and Anar | - | Done
2 | Feedback info | Abdoul: all good thanks Make sure the final result aligns with the defined KPIs (Key Performance Indicators) and meets the expected objectives. | Hans and Anar | - | Done
3 | Feedback info | Esther: get well soon | Hans and Anar | - | Done
4 | Feedback info | Phares: all good thanks Before adding the remaining features, make sure that everything currently implemented works correctly. Test the existing functionality and resolve any issues before moving forward. This will help ensure a stable and reliable final module. | Hans and Anar | - | Done
5 | Feedback info | Rayanne: your voice was a bit low, about what machinery you are talking of your backend looks more mature now | Hans and Anar | - | Done
6 | Feedback info | Madiega: all good – what is a Spring Boot make sure evrything works | Hans and Anar | - | Done
7 | Feedback info | Carine: all good – will explained by using the word “Visitor management”, it is well understood what it is all about: | Hans and Anar | - | Done
8 | Feedback info | Christelle: all good what are your sensors actually measuring; good Logo but maybe storing Mangos would be an even better picture add more Expand your backend by adding more entities (the different types of data or objects in your system) and relationships (the connections between them). | Hans and Anar | - | Done
9 | Feedback info | Mariata: all good; what are all pages | Hans and Anar | - | Done
10 | Feedback info | Tania: all good; what security do you mean – security of access Make sure to test the entire workflow from start to finish, ensuring that all components work together correctly. | Hans and Anar | - | Done
10 | 18.09.2026 | Hans Ehm, Abdelgafar Ismail, Excellence program Students , Botho Schanze, Tim , Hans , Wilfried , Ana…. | Name(s) of responsible(s) | DD.MM.YYYY
Item # | Item Type | Topics | Owners | Deadline | Status | Comments | Links
1 | Info | General Feedback Coordinate with the other team members Make sure you communicate and coordinate with the people working on the other parts of the project, especially the backend team. The goal is to ensure that your module can be smoothly integrated into the final product without compatibility or integration issues.. | Abdo and Anar | - | Done
2 | Feedback info | Mariata: very good presentation, organized updates – where is the API data coming from? | Abdo and Anar | - | Done
3 | Feedback info | Ben: very good presentation, organized updates – very good that you managed to meet an expert regarding product transformation, it is always useful to get hands-on and real-world insights | Abdo and Anar | - | Done
4 | Feedback info | Phares: get well soon | Abdo and Anar | - | Done
5 | Feedback info | Rayane: very good presentation, organized updates – clear progress and next steps – are you considering input from other modules e.g. plants to estimate expected load | Abdo and Anar | - | Done
6 | Feedback info | Justine: very good presentation, organized updates – how will your BE integrate input from other module e.g. equipment energy consumption and make forecasting | Abdo and Anar | - | Done
7 | Feedback info | Carine: very good presentation, organized updates – clear next steps as well | Abdo and Anar | - | Done
8 | Feedback info | Christelle: get well soon | Abdo and Anar | - | Done
9 | Feedback info | Tania: very good presentation, organized updates – clear next steps and aligned with the plan | Abdo and Anar | - | Done
10 | Feedback info | Esther: very good presentation, organized updates – how to prepare input to all other modules based on amount of mango harvested for e.g. | Abdo and Anar | - | Done
11 | 25.09.2026 | Hans Ehm, Abdelgafar Ismail, Excellence program Students , Botho Schanze, Tim , Hans , Wilfried , Ana…. | Name(s) of responsible(s) | DD.MM.YYYY
Item # | Item Type | Topics | Owners | Deadline | Status | Comments | Links
1 | Info | General Feedback Coordinate with the other team members Make sure you communicate and coordinate with the people working on the other parts of the project, especially the backend team. The goal is to ensure that your module can be smoothly integrated into the final product without compatibility or integration issues.. | Anar | - | Done
2 | Feedback info | Phares: Coordinate with the other team members and have them review your work to ensure everything works correctly. Also, update the calendar week/date on your homepage, as it is currently out of date. | Anar | - | Done
3 | Feedback info | Rayane: Clearly define how spare parts are linked to the other entities/modules. | Anar | - | Done
4 | Feedback info | Esther: Coordinate with the other team members and have them review your work to ensure everything works correctly and would work smoothly with the other modules before final integration. | Anar | - | Done
5 | Feedback info | Marieta:Coordinate with the other team members and have them review your work to ensure everything works correctly and would work smoothly with the other modules before final integration. | Anar | - | Done
6 | Feedback info | Carine:Coordinate with the other team members and have them review your work to ensure everything works correctly and would work smoothly with the other modules before final integration. | Anar | - | Done
7 | Feedback info | Tania: Coordinate with the other team members and have them review your work to ensure everything works correctly and would work smoothly with the other modules before final integration. | Anar | - | Done
8 | Feedback info | Justine: Coordinate with the other team members and have them review your work to ensure everything works correctly and would work smoothly with the other modules before final integration. | Anar | - | Done
9 | Feedback info | Abdoul:Coordinate with the other team members and have them review your work to ensure everything works correctly and would work smoothly with the other modules before final integration. | Anar | - | Done
10 | Feedback info | Christelle: Not in the call | Anar | - | Done
12 | 02.09.2026 | Excellence program Students , Tim , Wilfried , . | Name(s) of responsible(s) | DD.MM.YYYY
Item # | Item Type | Topics | Owners | Deadline | Status | Comments | Links
1 | Info | General Feedback Coordinate with the other team members Make sure you communicate and coordinate with the people working on the other parts of the project, especially the backend team. The goal is to ensure that your module can be smoothly integrated into the final product without compatibility or integration issues.. | Anar | - | Done
2 | Feedback info | Justine: Your homepage update section contains too much text. Summarize the main achievements and explain them briefly and concisely.: Coordinate with the other team members and have them review your work to ensure everything works correctly. Also, update the calendar week/date on your homepage, as it is currently out of date. | Anar | - | Done
3 | Feedback info | Phares: Good job resolving the conflict on GitHub. Continue progressing proactively without waiting for feedback before moving forward. | Anar | - | Done
4 | Feedback info | Esther: Continue progressing with your work without being dependent on feedback from your teammates before moving forward. | Anar | - | Done
5 | Feedback info | Marieta:CAbdoul:Continue progressing with your work without being dependent on feedback from your teammates before moving forward. | Anar | - | Done
6 | Feedback info | Abdoul:Continue progressing with your work without being dependent on feedback from your teammates before moving forward. | Anar | - | Done
7 | Feedback info | Tania: Your presentation was brief. Go deeper into your tasks, progress, and achievements. | Anar | - | Done
8 | Feedback info | Christelle: Continue progressing with your work without being dependent on feedback. | Anar | - | Done
9 | Feedback info | Rayane: not in the call | Anar | - | Done
10 | Feedback info | Carine: not in the call | Anar | - | Done
13 | 02.09.2026 | Excellence program Students , Tim , Wilfried ,Linus . | Name(s) of responsible(s) | DD.MM.YYYY
Item # | Item Type | Topics | Owners | Deadline | Status | Comments | Links
1 | Info | General Feedback Coordinate with the other team members Make sure you communicate and coordinate with the people working on the other parts of the project, especially the backend team. The goal is to ensure that your module can be smoothly integrated into the final product without compatibility or integration issues.. | All | - | Done
2 | Feedback info | Abdoul: great work on cross module testing | Tim | - | Done
3 | Feedback info | Esther: very good progress | Tim | - | Done
4 | Feedback info | Tania: thanks for the update; next week feel free to go into some more details on your progress as well as integration with other modules | Tim | - | Done
5 | Feedback info | Phares: Good progress overall, but please speak a little louder and more clearly, as you were sometimes difficult to hear. | Tim | - | Done
6 | Feedback info | Justine: thanks for the great progress update | Tim | - | Done
7 | Feedback info | Christelle: great presentation; ensure close coordination with all dependent module owners | Tim | - | Done
8 | Feedback info | Mariata: thanks for the update; next week feel free to elaborate more on specific advancements and make written progress report less generic | Tim | - | Done
9 | Feedback info | Rayane: not in the call | Tim | - | Done
10 | Feedback info | Carine: not in the call | Tim | - | Done

## Instructions
Instructions
Status for A/I (action items) | Explanation
Open | A/I not started yet
Ongoing | A/I is started, not finished
Done | A/I finished
How to add a new meeting:
Ctrl+C an earlier meeting (one whole table from grey to next grey)
Right-click on cell 2A (row below "Project name") and select "Insert copied cells"
Select "Shift cells down"
Replace information
Add rows if needed, and delete empty rows
Write item # manually (First item # first meeting = 1. First item # meeting n = last item # previous meeting +1)
the status of decision and information can only be “Done”. You can have “Open” or “Ongoing” only for an action item. Also, each item should have an owner. In case of an action item, the owner is the one who has to do the work. In case of decision or information, it can be one person or all attendees.
The status of decision and information can only be “Done”. You can have “Open” or “Ongoing” only for an action item. Also, each item should have an owner. In case of an action item, the owner is the one who has to do the work. In case of decision or information, it can be one person or all attendees.